## LESSONS LEARNED
LESSONS LEARNED
PROJECT NAME | Recommnder System
PROJECT ID
PROJECT MANAGER | Jayanth G S
PROJECT SPONSOR | Cloud Counselage Pvt Ltd
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2020-06-16 | Attempt to understand the data exploration techniques using Plotly Express | Technical | None | Plotly express is a must tool for EDA and should be learned at an early stage of ML |  | Project Manager | Complete
2 | 2020-07-08 | Understanding Named Entity Recognition and its used cases | Technical | None | Current Solution is completely NER based but it is suggested to combine this technique with a DL approach which I wasn’t able to complete | Combining the current approach with a deep learning approach | Project Manager | Left
3 | 2020-07-17 | Understanding the different terms present in the SRS document | Documentation | None |  | Prepared a detailed SRS covering all the main points required | Project Manager | Complete
4 | 2020-07-20 | Built a script for creating a dataset for NER using spacy | Technical | Time for creating a dataset for long so I attempted to automate it | The script could be improved since it requires some amount of manual annotation |  | Project Manager | In progress
5 | 2020-07-22 | Worked on building a python script which takes minimum time to execute making sure of maintaining min time complexity | Technical | Program was taking more time to execute which needed to be reduced | Use pandas functions to furthur reduce the time of execution | Use pandas functions to furthur reduce the time of execution | Project Manager | Left