## DEVELOPMENT LOG
DEVELOPMENT LOG
PROJECT NAME | Recommendation system for domain and events
PROJECT ID
PROJECT MANAGER | Jayanth G S
DOCUMENT VERSION | 1
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 2020-07-31
SL NO | FEATURE NAME | VERSION 1 LINK | VERSION 1 CREATION DATE | VERSION 2 LINK | VERSION 2 CREATION DATE | VERSION CHANGE DESCRIPTION | DEVELOPMENT STATUS | REVIEW STATUS | COMMENTS
1 | Performing EDA | https://github.com/ELITA04/Recommender_system/tree/master/EDA | 2020-06-16 |  |  |  | Completed
2 | Dataset for model training - BERT | https://github.com/ELITA04/Recommender_system/tree/master/Dataset/Code/K_TRAIN | 2020-07-09 | https://github.com/ELITA04/Recommender_system/tree/master/Dataset/Code/K_TRAIN | 2020-07-15 | very little flexiblity in terms of sentence generation | Completed
3 | Attempt to train on BERT model | https://github.com/ELITA04/Recommender_system/blob/master/NER/approach1.py | 2020-07-11 | https://github.com/ELITA04/Recommender_system/blob/master/NER/approach1.py | 2020-07-15 | model performance poor as it is misclassifying | Completed
4 | Dataset for model training - spaCy | https://github.com/ELITA04/Recommender_system/tree/master/Dataset/Code/spaCy | 2020-07-18 | https://github.com/ELITA04/Recommender_system/tree/master/Dataset/Code/spaCy | 2020-07-20 | extracted sentence from LinkedIn | Completed
5 | Attempt to use spaCy for NER | https://github.com/ELITA04/Recommender_system/blob/master/NER/approach2.py | 2020-07-15 | https://github.com/ELITA04/Recommender_system/blob/master/NER/approach2.py |  | model classifying good amount of intents, can do better using more data | Completed
6 | Script which uses the saved model for employee extraction | https://github.com/ELITA04/Recommender_system/blob/master/Scripts/saving.py | 2020-07-22 |  |  |  | Completed