## Sheet1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Recommeder system based on domain and events.
PROJECT SPONSOR | Cloud Counselage Pvt. Ltd.
PROJECT MANAGER | Jayanth G S
EXPECTED START DATE | 2020-06-15
EXPECTED COMPLETION DATE | 2020-07-31
ESTIMATED COST
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | • To build a recommeder system that classifies a given event into one or more domains. • To fetch the employee from the employee database that matches these preferences. • Create a csv of these matching employees.
BUSINESS CASE | One often misses events of interest sheerly due to a lack of awareness at the right time. Cloud Counselage also receives invites for events in multiple domains that need to be forwarded to people with relevant interests. The aim is to create a Recommender System that recommends only relevant events to each employee and intern based on their preferences, whenever the company receives invites for said events. The system should read new events and autonomously classify them into various domains. It should then match the event with all of those in the company database who have given said domains as a preference. Finally, for each event, the system should output the list of people whose preferences match with the event’s detected domain.
GOALS/METRICS | • To create a dataset with text input of potential events so that the model learns well and doesnt underfit. • To understand the underling idea behind BERT for named entity recognition and put in practise. • To design a robust solution to classify the domain and events for recommending according to the liking of an individual.
EXPECTED DELIVERABLES | • To read a set of events as input and to classify each event into one or more domains. • To fetch the employee database with domain and event preferences.and to match each event with all interested employees. • To output the list of matching employees per event.
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | • To build a recommeder system that classifies a given event into one or more domains. • To fetch the employee from the employee database that matches these preferences. • Create a csv of these matching employees.
OUTSIDE OF SCOPE | • Could be futher automated by creating an email script where the event mail directly goes to the employee. • Currently the input is in the form of text, this could be changed and a poster of the event or pdf could be provided as input.
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Elita Menezes
SUPPORT RESOURCES | Laptop, Internet connection, dataset-(self made)
SPECIAL NEEDS | GPU for training.
PROJECT BENEFITS AND CUSTOMERS
PROCESS OWNER | Elita Menezes
KEY STAKEHOLDERS | Jayanth G S, Nirbhey Singh Pahwa
END CUSTOMER | Cloud Counselage Pvt. Ltd.
EXPECTED BENEFIT | 1. Fully automated recommender, reduces human effort. 2. Encourages employees to events of their liking and in turn increasing their productivity.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS | Due to insufficient training examples there may be a possibility it may classify some events as 'OTHER' causing missed opporunity for potential employees.
ASSUMPTIONS | 1. A well defined dataset with a good number of training examples that covers all types of event entries. 2. Input will be in the form of text and not an image/pdf.
CONSTRAINTS | 1. The dataset may have a wide variety of sentences since it is the thought process of an individual and thus may not cover some event terms. 2. Training of the model will be done on google colab using the 25 gb GPU provided, due to absence of GPU on personal laptop.