## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME | Recommendation system
PROJECT MANAGER | Jayanth G S |  | EXECUTION PHASE START DATE:
PROJECT DELIVERABLE | Script for recommedation system |  | EXECUTION PHASE END DATE:
PROJECT SCOPE
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 2020-07-31
OVERALL PROGRESS | In progress
PARENT FEATURE | FEATURES | REQUIRED TIME (IN HRS) | START DATE | END DATE | DURATION IN DAYS | STATUS
1. Understanding the problem statement
| 1.1 Research about the problem statement | 4 | 2020-06-16 | 2020-06-20 | 2 | COMPLETED
| 1.2 Going through the documents provided | 3 | 2020-06-17 | 2020-06-18 | 1.5 | COMPLETED
2. Prepraring the Project Charter, SRS and development model
| 2.1 Understand the terms used in an SRS | 2 | 2020-06-17 | 2020-06-17 | 2 | COMPLETED
| 2.2 Research about concepts related to project charter | 2 | 2020-06-18 | 2020-06-18 | 2 | COMPLETED
| 2.3 Building the SRS document | 4 | 2020-06-19 | 2020-06-20 | 2 | COMPLETED
| 2.4 Building the project charter | 4 | 2020-06-21 | 2020-06-22 | 2 | COMPLETED
| 2.5 Creating charts for design model | 2 | 2020-06-22 | 2020-06-22 | 2 | COMPLETED
| 2.6 Building design model document | 1 | 2020-06-23 | 2020-06-23 | 1 | COMPLETED
| 2.7 Understanding more about the problem statement | 1 | 2020-06-25 | 2020-06-25 | 1 | COMPLETED
| 2.8 Researching about the problem statement | 6 | 2020-09-27 | 2020-09-29 | 3 | COMPLETED
3. Dataset Building phase
| 3.1 Build a baseline dataset (BERT) | 6 | 2020-07-09 | 2020-07-10 | 3 | COMPLETED
| 3.2 Work on bringing varitations to the dataset (BERT) | 3 | 2020-07-15 | 2020-07-15 | 3 | COMPLETED
| 3.3 Building a basline dataset (spaCy) - LinkedIn post | 4 | 2020-07-17 | 2000-07-18 | 2 | COMPLETED
| 3.4 Working on variations on dataset (spaCy) | 5 | 2020-09-20 | 2020-09-20 | 5 | COMPLETED
4. Developing model for Named Entity Recognition
| 4.1 Building BERT model | 2 | 2020-07-11 | 2020-02-11 | 2 | COMPLETED
| 4.2 Fine Tuning BERT | 1 | 2020-07-12 | 2020-07-12 | 1 | COMPLETED
| 4.3 Training on model with variations | 2 | 2020-07-15 | 2020-07-15 | 2 | COMPLETED
| 4.4 Training initial spaCy model | 2 | 2020-07-19 | 2020-07-19 | 2 | COMPLETED
| 4.5 Retraining on better dataset | 1 | 2020-02-21 | 2020-02-21 | 1 | COMPLETED
5.Script for extracting
| 5.1 Script reading csv of employee and checking for matching domain and events | 2.5 | 2020-07-22 | 2020-07-22 | 2.5 | COMPLETED
6. Testing Phase