## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 3 | 0 | 0 | 0 | 0 | 0
| Project title: | Recommendation system based on domain and events |  | Project Id: | 2678 | Project Manager: | Jayanth G S |  |  | Assumption | 2 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 2 | 0 | 0 | 0 | 0 | 0
|  |  |  | Last Updated date: | 2020-07-25 | Project Team Lead: | Aarya Bodhankar |  |  | Dependency | 1 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 8 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Assumption | Covering all possible examples in dataset | training of the model | Trying to create a diversified dataset with synonyms | Project Manager | Critical |  | Closed | Risk
2 | Risk | A dataset with less examples | affects the model training | Trying to collect more examples for training | Project Manager | Critical |  | Closed | Assumption
3 | Risk | Fine tuning the BERT model | creates a better model | Fine tuning the model by changing few parameters | Project Manager | Low |  | Closed | Issue
4 | Issue | BERT model not giving good results | domain and events are not being classified correctly | Try other NER methods for classification | Project Manager | Negligible |  | Closed | Dependency
5 | Assumption | spaCy giving decent result with 50 sentences as training | domain and events are being classified correctly 50% times | Working on building a dataset with much more training examples | Project Manager | Moderate |  | Closed
6 | Issue | If a domain or event is not extracted | Assignment to employee will be incorrect | Working on building a fail safe | Project Manager | High |  | Closed | Open
7 | Dependency | Fail Safe for extraction | Using difflib helps getting the words closest to the domain and events |  | Project Manager | High |  | Closed | Closed
8 | Risk | Covering "other" domain examples | May miss the other class | Build a dataset with egs of other | Project Manager | Critical |  | Closed
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24